## 🏠 Dashboard
🚀 100-Day SaaS WorkHub Challenge
Multi-Tenant Project Management SaaS ¦ .NET + React + PostgreSQL + SignalR
Phase | Name | Days | Duration | Tasks | Goal
Phase 1 | PHASE 1 — Setup & Core Backend | Day 1–15 | 15 days | 15 | Strong backend foundation + auth
Phase 2 | PHASE 2 — Project & Task System | Day 16–30 | 15 days | 15 | Core product functionality
Phase 3 | PHASE 3 — Frontend Core | Day 31–50 | 20 days | 20 | Functional UI + API integration
Phase 4 | PHASE 4 — Fullstack Features | Day 51–65 | 15 days | 15 | Make it feel like a real product
Phase 5 | PHASE 5 — Real-Time & Advanced | Day 66–80 | 15 days | 15 | Stand out features
Phase 6 | PHASE 6 — DevOps & Deployment | Day 81–90 | 10 days | 10 | Production-ready app
Phase 7 | PHASE 7 — Polish & Portfolio | Day 91–100 | 10 days | 10 | Make it job-winning
⚙️ TECH STACK
Backend | .NET 8 Web API, ASP.NET Core, EF Core, SignalR, Serilog, FluentValidation
Database | PostgreSQL, Redis (caching), EF Core Migrations
Auth & Security | JWT Bearer tokens, Refresh tokens, BCrypt, Role-based authorization
Frontend | React 18, Vite, Tailwind CSS, React Router v6, TanStack Query, Axios
UI Libraries | dnd-kit (drag & drop), Recharts (charts), React Hook Form, Zod
DevOps | Docker, GitHub Actions CI/CD, Render/Railway (API), Vercel (Frontend)
Storage | AWS S3 / Cloudinary (files), Supabase / Neon (PostgreSQL cloud)
📊 PROGRESS TRACKER — Update the STATUS column in each phase sheet
Phase | Total Tasks | Done | In Progress | Blocked | % Complete
Phase 1 | 15 | 0 | 0 | 0 | 0%
Phase 2 | 15 | 0 | 0 | 0 | 0%
Phase 3 | 20 | 0 | 0 | 0 | 0%
Phase 4 | 15 | 0 | 0 | 0 | 0%
Phase 5 | 15 | 0 | 0 | 0 | 0%
Phase 6 | 10 | 0 | 0 | 0 | 0%
Phase 7 | 10 | 0 | 0 | 0 | 0%
🎯 KEY MILESTONES
Day 15 | ✅ Full auth system working (register, login, JWT, roles, multi-tenancy)
Day 30 | ✅ Complete project & task API with filtering, pagination, activity logs
Day 50 | ✅ Full frontend — dashboard, kanban board, drag & drop, React Query
Day 65 | ✅ Production-like app with notifications, invites, search, permissions
Day 80 | ✅ Real-time chat + SignalR notifications + file uploads + analytics charts
Day 90 | ✅ Dockerized, deployed to cloud, CI/CD pipeline live
Day 100 | 🏆 Portfolio-ready full-stack SaaS — README, demo video, deployed URL

## Phase 1
Phase 1 ¦ PHASE 1 — Setup & Core Backend
🎯 Goal: Strong backend foundation + auth ¦ 📅 Day 1 – 15 ¦ 📋 15 tasks
Day | Task / Feature | Details & Sub-steps | Status | Priority | Category | Tools / Tech | Notes
Day 1 | Create GitHub repo | Setup .NET Web API project, Setup PostgreSQL | Done | High | Env Setup | GitHub, .NET CLI, PostgreSQL
Day 2 | Design DB Schema | Design Users, Organizations, Roles tables | Done | High | Database | PostgreSQL, draw.io
Day 3 | Create ER Diagram | Visual diagram of all entities and relations | Done | Medium | Database | draw.io / dbdiagram.io
Day 4 | DB Connection | Setup connection string, DbContext, migrations | Done | High | Database | .NET EF Core
Day 5 | Base Models | Create User, Organization C# models | Done | High | Backend | C#, EF Core
Day 6 | User Registration | POST /auth/register with validation | Done | High | Auth | ASP.NET Core
Day 7 | Password Hashing | Implement bcrypt hashing for passwords | Done | High | Security | BCrypt.Net
Day 8 | Login API + JWT | POST /auth/login returning JWT token | Done | High | Auth | Microsoft.IdentityModel.Tokens
Day 9 | Refresh Token | Implement refresh token rotation system | Not Started | High | Auth | ASP.NET Core
Day 10 | Auth Middleware | Middleware to validate JWT on protected routes | Not Started | High | Auth | ASP.NET Core Middleware
Day 11 | Role System | Owner, Admin, Member roles with permissions | Not Started | High | Auth | Custom roles
Day 12 | AuthZ Middleware | Authorization middleware using roles | Not Started | High | Security | ASP.NET Core
Day 13 | Org Creation | POST /organizations — create org | Not Started | High | Backend | ASP.NET Core
Day 14 | Join Org Flow | Invite/join organization logic | Not Started | Medium | Backend | ASP.NET Core
Day 15 | Multi-Tenancy | Org-based data isolation via TenantId | Not Started | High | Architecture | EF Core Global Filters
💡 TIP: Commit every day to GitHub. Even small changes. This builds your streak & portfolio.

## Phase 2
Phase 2 ¦ PHASE 2 — Project & Task System
🎯 Goal: Core product functionality ¦ 📅 Day 16 – 30 ¦ 📋 15 tasks
Day | Task / Feature | Details & Sub-steps | Status | Priority | Category | Tools / Tech | Notes
Day 16 | Seed Test Data | Add seed data for dev testing | Not Started | Medium | Database | EF Core DataSeeder
Day 17 | Test All APIs | Postman collection for all Phase 1 endpoints | Not Started | High | Testing | Postman
Day 18 | Project Entity | Project model + migration | Not Started | High | Backend | EF Core
Day 19 | Task Entity | Task model with FK to Project + User | Not Started | High | Backend | EF Core
Day 20 | Project CRUD APIs | GET/POST/PUT/DELETE /projects | Not Started | High | Backend | ASP.NET Core
Day 21 | Task CRUD APIs | GET/POST/PUT/DELETE /tasks | Not Started | High | Backend | ASP.NET Core
Day 22 | Assign Users to Tasks | PATCH /tasks/{id}/assign endpoint | Not Started | High | Backend | ASP.NET Core
Day 23 | Task Status System | todo, in-progress, done status enum | Not Started | High | Backend | C# Enum
Day 24 | Priority & Deadlines | Priority field + DueDate on Task | Not Started | Medium | Backend | EF Core
Day 25 | Filtering & Sorting | Query params: ?status=todo&sort=priority | Not Started | Medium | Backend | LINQ
Day 26 | Pagination | Generic PagedResult<T> response wrapper | Not Started | Medium | Backend | LINQ Skip/Take
Day 27 | Comments on Tasks | Comment entity + CRUD APIs | Not Started | Medium | Backend | EF Core
Day 28 | Activity Log | Auto-log create/update/delete actions | Not Started | Medium | Backend | EF Core Interceptors
Day 29 | Validation DTOs | FluentValidation for all request models | Not Started | High | Quality | FluentValidation
Day 30 | Global Error Handling | Middleware returning ProblemDetails on errors | Not Started | High | Quality | ASP.NET Core
💡 TIP: Write Postman tests for every endpoint you build. It saves debugging time later.

## Phase 3
Phase 3 ¦ PHASE 3 — Frontend Core
🎯 Goal: Functional UI + API integration ¦ 📅 Day 31 – 50 ¦ 📋 20 tasks
Day | Task / Feature | Details & Sub-steps | Status | Priority | Category | Tools / Tech | Notes
Day 31 | Logging (Serilog) | Structured logging with Serilog + file sink | Done | Medium | Quality | Serilog
Day 32 | Clean Architecture | Refactor to Domain/Application/Infrastructure layers | Done | High | Architecture | Clean Arch pattern
Day 33 | React + Tailwind Setup | Vite + React + Tailwind CSS project init | Done | High | Frontend | Vite, Tailwind CSS
Day 34 | Folder Structure | feature-based folder layout | Done | Medium | Frontend | React
Day 35 | Routing Setup | React Router v6 routes config | Not Started | High | Frontend | React Router
Day 36 | Auth Pages UI | Login and Register page components | Not Started | High | Frontend | React, Tailwind
Day 37 | Connect Auth APIs | Axios calls to login/register endpoints | Not Started | High | Frontend | Axios
Day 38 | Token Storage + Auth Context | localStorage tokens + React Context | Not Started | High | Frontend | React Context
Day 39 | Protected Routes | Route guard redirecting unauthenticated users | Not Started | High | Frontend | React Router
Day 40 | Dashboard Layout | Sidebar + top nav + main area shell | Not Started | High | Frontend | React, Tailwind
Day 41 | Organization UI | Org info card + member list | Not Started | Medium | Frontend | React
Day 42 | Project List UI | Card grid of projects | Not Started | Medium | Frontend | React
Day 43 | Task List UI | Table/list view of tasks with status badges | Not Started | High | Frontend | React
Day 44 | Create/Edit Task Forms | Modal forms with validation | Not Started | High | Frontend | React
Day 45 | React Query Integration | useQuery + useMutation for all APIs | Not Started | High | Frontend | TanStack Query
Day 46 | Loading + Error States | Skeleton loaders + error boundaries | Not Started | Medium | Frontend | React
Day 47 | Kanban Board UI | 3-column board (todo/progress/done) | Not Started | High | Frontend | React
Day 48 | Drag & Drop | dnd-kit drag between kanban columns | Not Started | Medium | Frontend | dnd-kit
Day 49 | Task Details Page | Full task page with metadata + comments | Not Started | High | Frontend | React
Day 50 | Comments UI | Add/view comments on task page | Not Started | Medium | Frontend | React
💡 TIP: Start with mobile-first design in Tailwind. Use sm/md/lg breakpoints consistently.

## Phase 4
Phase 4 ¦ PHASE 4 — Fullstack Features
🎯 Goal: Make it feel like a real product ¦ 📅 Day 51 – 65 ¦ 📋 15 tasks
Day | Task / Feature | Details & Sub-steps | Status | Priority | Category | Tools / Tech | Notes
Day 51 | Activity Log UI | Timeline feed of task activities | Not Started | Medium | Frontend | React
Day 52 | UI Polish + Responsive | Mobile-friendly layout + spacing fixes | Not Started | High | Frontend | Tailwind CSS
Day 53 | Role-Based UI Access | Hide/show UI elements by role | Not Started | High | Frontend | React Context
Day 54 | Permission Checks | Frontend + backend permission validation | Not Started | High | Security | ASP.NET Core + React
Day 55 | API Error Handling | Global Axios interceptor for 401/403/500 | Not Started | High | Frontend | Axios
Day 56 | Form Validation | React Hook Form + Zod schema validation | Not Started | High | Frontend | React Hook Form, Zod
Day 57 | Search Functionality | Search tasks/projects by keyword | Not Started | Medium | Feature | LINQ + React
Day 58 | User Profile Page | View/edit own profile info | Not Started | Medium | Feature | React
Day 59 | Invite Users to Org | Email invite link flow | Not Started | High | Feature | ASP.NET Core
Day 60 | Email Sending | Send invite/notification emails | Not Started | Medium | Feature | SendGrid / MailKit
Day 61 | Notification DB Model | Notification entity + migration | Not Started | High | Feature | EF Core
Day 62 | Notification API | GET /notifications + mark-as-read | Not Started | High | Feature | ASP.NET Core
Day 63 | Notification UI | Bell icon dropdown with notifications | Not Started | High | Frontend | React
Day 64 | Mark as Read | Click to mark notification read | Not Started | Medium | Frontend | React
Day 65 | Backend Optimization | Add DB indexes, optimize slow queries | Not Started | Medium | Performance | PostgreSQL
💡 TIP: React Query caches API results — use it for all server state, avoid useState for API data.

## Phase 5
Phase 5 ¦ PHASE 5 — Real-Time & Advanced
🎯 Goal: Stand out features ¦ 📅 Day 66 – 80 ¦ 📋 15 tasks
Day | Task / Feature | Details & Sub-steps | Status | Priority | Category | Tools / Tech | Notes
Day 66 | Code Cleanup | Remove dead code, consistent naming | Not Started | Medium | Quality | Manual
Day 67 | Full System Testing | End-to-end test all features manually | Not Started | High | Testing | Postman + Browser
Day 68 | Setup SignalR | Add SignalR hub to backend | Not Started | High | Real-Time | ASP.NET Core SignalR
Day 69 | Real-Time Notifications | Push notifications via SignalR | Not Started | High | Real-Time | SignalR + React
Day 70 | Chat DB Design | Message, ChatRoom entities | Not Started | High | Feature | EF Core
Day 71 | Chat Backend APIs | REST APIs for chat history | Not Started | High | Feature | ASP.NET Core
Day 72 | Real-Time Chat | SignalR hub for live messaging | Not Started | High | Real-Time | SignalR
Day 73 | Chat UI | Chat panel component | Not Started | High | Frontend | React
Day 74 | Online/Offline Status | Track user presence via SignalR | Not Started | Medium | Feature | SignalR
Day 75 | Typing Indicator | Broadcast typing events via hub | Not Started | Medium | Feature | SignalR
Day 76 | File Upload Setup | Multipart upload endpoint | Not Started | High | Feature | ASP.NET Core
Day 77 | Attach Files to Tasks | Upload + link file to task | Not Started | High | Feature | ASP.NET Core
Day 78 | File Storage | Store files locally or S3/Cloudinary | Not Started | High | Infrastructure | AWS S3 / local
Day 79 | Analytics API | Task counts, completion rate, user stats | Not Started | Medium | Feature | LINQ aggregations
Day 80 | Charts UI | Bar/pie charts using Recharts | Not Started | Medium | Frontend | Recharts
💡 TIP: SignalR groups = rooms. Put users in org-specific groups for targeted real-time events.

## Phase 6
Phase 6 ¦ PHASE 6 — DevOps & Deployment
🎯 Goal: Production-ready app ¦ 📅 Day 81 – 90 ¦ 📋 10 tasks
Day | Task / Feature | Details & Sub-steps | Status | Priority | Category | Tools / Tech | Notes
Day 81 | Redis Caching | Cache frequent queries with Redis | Not Started | Medium | Performance | StackExchange.Redis
Day 82 | Performance Optimization | Profile + fix slow endpoints | Not Started | High | Performance | MiniProfiler
Day 83 | Learn Docker Basics | Containers, images, Dockerfile concepts | Not Started | High | DevOps | Docker
Day 84 | Dockerize Backend | Write Dockerfile for .NET API | Not Started | High | DevOps | Docker
Day 85 | Dockerize Frontend | Write Dockerfile for React app | Not Started | High | DevOps | Docker
Day 86 | Environment Variables | Setup .env + secrets management | Not Started | High | DevOps | Docker / dotenv
Day 87 | Deploy Backend | Deploy API to Render or Railway | Not Started | High | Deployment | Render / Railway
Day 88 | Deploy Frontend | Deploy React app to Vercel | Not Started | High | Deployment | Vercel
Day 89 | Cloud PostgreSQL | Setup managed DB (Supabase / Neon) | Not Started | High | Infrastructure | Supabase
Day 90 | CI/CD Pipeline | GitHub Actions: build + test + deploy | Not Started | High | DevOps | GitHub Actions
💡 TIP: Always test your Docker image locally before deploying. docker run -p 5000:80 your-image

## Phase 7
Phase 7 ¦ PHASE 7 — Polish & Portfolio
🎯 Goal: Make it job-winning ¦ 📅 Day 91 – 100 ¦ 📋 10 tasks
Day | Task / Feature | Details & Sub-steps | Status | Priority | Category | Tools / Tech | Notes
Day 91 | Domain + HTTPS | Custom domain + SSL certificate | Not Started | High | Deployment | Vercel / Cloudflare
Day 92 | E2E Production Test | Test all flows on live production URL | Not Started | High | Testing | Browser
Day 93 | Bug Fixes | Fix all known bugs from testing | Not Started | High | Quality | Manual
Day 94 | UI/UX Improvements | Polish animations, spacing, micro-interactions | Not Started | High | Frontend | Tailwind / Framer
Day 95 | Query Optimization | Add missing indexes + review N+1 queries | Not Started | Medium | Performance | PostgreSQL EXPLAIN
Day 96 | Security Review | XSS, CSRF, input sanitization review | Not Started | High | Security | OWASP checklist
Day 97 | Write README | Setup, architecture, screenshots, API docs | Not Started | High | Portfolio | Markdown
Day 98 | Architecture Diagram | System diagram showing all components | Not Started | Medium | Portfolio | draw.io
Day 99 | Record Demo Video | 2-3 min walkthrough of the product | Not Started | High | Portfolio | Loom / OBS
Day 100 | Portfolio Website + Final Deploy | Add project to portfolio, share on LinkedIn/GitHub | Not Started | High | Portfolio | React / Next.js
💡 TIP: Your README is your first interview. Include: demo link, screenshots, setup steps, architecture.

## 📅 Timeline
📅 100-Day Project Timeline
| W1 | [9 empty] | W2 | [9 empty] | W3 | [9 empty] | W4 | [9 empty] | W5 | [9 empty] | W6 | [9 empty] | W7 | [9 empty] | W8 | [9 empty] | W9 | [9 empty] | W10
Phase / Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100
PHASE 1 — Setup & Core Backend
Day 1: Create GitHub repo | ●
Day 2: Design DB Schema |  | ●
Day 3: Create ER Diagram |  |  | ●
Day 4: DB Connection |  |  |  | ●
Day 5: Base Models |  |  |  |  | ●
Day 6: User Registration | [5 empty] | ●
Day 7: Password Hashing | [6 empty] | ●
Day 8: Login API + JWT | [7 empty] | ●
Day 9: Refresh Token | [8 empty] | ●
Day 10: Auth Middleware | [9 empty] | ●
Day 11: Role System | [10 empty] | ●
Day 12: AuthZ Middleware | [11 empty] | ●
Day 13: Org Creation | [12 empty] | ●
Day 14: Join Org Flow | [13 empty] | ●
Day 15: Multi-Tenancy | [14 empty] | ●
PHASE 2 — Project & Task System
Day 16: Seed Test Data | [15 empty] | ●
Day 17: Test All APIs | [16 empty] | ●
Day 18: Project Entity | [17 empty] | ●
Day 19: Task Entity | [18 empty] | ●
Day 20: Project CRUD APIs | [19 empty] | ●
Day 21: Task CRUD APIs | [20 empty] | ●
Day 22: Assign Users to Tasks | [21 empty] | ●
Day 23: Task Status System | [22 empty] | ●
Day 24: Priority & Deadlines | [23 empty] | ●
Day 25: Filtering & Sorting | [24 empty] | ●
Day 26: Pagination | [25 empty] | ●
Day 27: Comments on Tasks | [26 empty] | ●
Day 28: Activity Log | [27 empty] | ●
Day 29: Validation DTOs | [28 empty] | ●
Day 30: Global Error Handling | [29 empty] | ●
PHASE 3 — Frontend Core
Day 31: Logging (Serilog) | [30 empty] | ●
Day 32: Clean Architecture | [31 empty] | ●
Day 33: React + Tailwind Setup | [32 empty] | ●
Day 34: Folder Structure | [33 empty] | ●
Day 35: Routing Setup | [34 empty] | ●
Day 36: Auth Pages UI | [35 empty] | ●
Day 37: Connect Auth APIs | [36 empty] | ●
Day 38: Token Storage + Auth Context | [37 empty] | ●
Day 39: Protected Routes | [38 empty] | ●
Day 40: Dashboard Layout | [39 empty] | ●
Day 41: Organization UI | [40 empty] | ●
Day 42: Project List UI | [41 empty] | ●
Day 43: Task List UI | [42 empty] | ●
Day 44: Create/Edit Task Forms | [43 empty] | ●
Day 45: React Query Integration | [44 empty] | ●
Day 46: Loading + Error States | [45 empty] | ●
Day 47: Kanban Board UI | [46 empty] | ●
Day 48: Drag & Drop | [47 empty] | ●
Day 49: Task Details Page | [48 empty] | ●
Day 50: Comments UI | [49 empty] | ●
PHASE 4 — Fullstack Features
Day 51: Activity Log UI | [50 empty] | ●
Day 52: UI Polish + Responsive | [51 empty] | ●
Day 53: Role-Based UI Access | [52 empty] | ●
Day 54: Permission Checks | [53 empty] | ●
Day 55: API Error Handling | [54 empty] | ●
Day 56: Form Validation | [55 empty] | ●
Day 57: Search Functionality | [56 empty] | ●
Day 58: User Profile Page | [57 empty] | ●
Day 59: Invite Users to Org | [58 empty] | ●
Day 60: Email Sending | [59 empty] | ●
Day 61: Notification DB Model | [60 empty] | ●
Day 62: Notification API | [61 empty] | ●
Day 63: Notification UI | [62 empty] | ●
Day 64: Mark as Read | [63 empty] | ●
Day 65: Backend Optimization | [64 empty] | ●
PHASE 5 — Real-Time & Advanced
Day 66: Code Cleanup | [65 empty] | ●
Day 67: Full System Testing | [66 empty] | ●
Day 68: Setup SignalR | [67 empty] | ●
Day 69: Real-Time Notifications | [68 empty] | ●
Day 70: Chat DB Design | [69 empty] | ●
Day 71: Chat Backend APIs | [70 empty] | ●
Day 72: Real-Time Chat | [71 empty] | ●
Day 73: Chat UI | [72 empty] | ●
Day 74: Online/Offline Status | [73 empty] | ●
Day 75: Typing Indicator | [74 empty] | ●
Day 76: File Upload Setup | [75 empty] | ●
Day 77: Attach Files to Tasks | [76 empty] | ●
Day 78: File Storage | [77 empty] | ●
Day 79: Analytics API | [78 empty] | ●
Day 80: Charts UI | [79 empty] | ●
PHASE 6 — DevOps & Deployment
Day 81: Redis Caching | [80 empty] | ●
Day 82: Performance Optimization | [81 empty] | ●
Day 83: Learn Docker Basics | [82 empty] | ●
Day 84: Dockerize Backend | [83 empty] | ●
Day 85: Dockerize Frontend | [84 empty] | ●
Day 86: Environment Variables | [85 empty] | ●
Day 87: Deploy Backend | [86 empty] | ●
Day 88: Deploy Frontend | [87 empty] | ●
Day 89: Cloud PostgreSQL | [88 empty] | ●
Day 90: CI/CD Pipeline | [89 empty] | ●
PHASE 7 — Polish & Portfolio
Day 91: Domain + HTTPS | [90 empty] | ●
Day 92: E2E Production Test | [91 empty] | ●
Day 93: Bug Fixes | [92 empty] | ●
Day 94: UI/UX Improvements | [93 empty] | ●
Day 95: Query Optimization | [94 empty] | ●
Day 96: Security Review | [95 empty] | ●
Day 97: Write README | [96 empty] | ●
Day 98: Architecture Diagram | [97 empty] | ●
Day 99: Record Demo Video | [98 empty] | ●
Day 100: Portfolio Website + Final Deploy | [99 empty] | ●

## 📋 Requirements
📋 SaaS WorkHub — Full System Requirements
🔐 Authentication & Security
User Registration | Email + password signup with validation | Must Have | Pending
JWT Authentication | Secure token-based login system | Must Have | Pending
Refresh Token Rotation | Extend sessions securely without re-login | Must Have | Pending
Password Hashing | BCrypt hashing before storing credentials | Must Have | Pending
Role-Based Access Control | Owner, Admin, Member with different permissions | Must Have | Pending
Multi-tenancy | Data isolation per organization via TenantId | Must Have | Pending
Auth Middleware | Validate JWT on every protected request | Must Have | Pending
🏢 Organization Management
Create Organization | User can create a new organization/workspace | Must Have | Pending
Invite Members | Invite via email link with token | Must Have | Pending
Join Organization | Accept invite and get assigned role | Must Have | Pending
Member Management | Owner can promote/demote/remove members | Should Have | Pending
Organization Settings | Update org name and settings | Should Have | Pending
📁 Project Management
Create Projects | Create project under an organization | Must Have | Pending
Edit/Delete Projects | Full CRUD for project management | Must Have | Pending
Project Members | Assign organization members to projects | Must Have | Pending
Project Status | Active / Archived project states | Should Have | Pending
✅ Task Management
Create Tasks | Add tasks within a project | Must Have | Pending
Edit/Delete Tasks | Full CRUD for task management | Must Have | Pending
Assign Users | Assign one or more members to a task | Must Have | Pending
Task Status | todo / in-progress / done workflow | Must Have | Pending
Priority Levels | Low / Medium / High priority tags | Must Have | Pending
Due Dates | Set deadlines on tasks | Must Have | Pending
Task Comments | Members can comment on tasks | Must Have | Pending
Activity Log | Auto-logged history of task changes | Should Have | Pending
File Attachments | Upload files and attach to tasks | Should Have | Pending
Filtering & Sorting | Filter by status, priority, assignee; sort by date | Must Have | Pending
Pagination | Paginated API responses for large datasets | Must Have | Pending
🎨 Frontend UI
Kanban Board | Drag-and-drop task board by status | Must Have | Pending
Dashboard | Overview of projects, tasks, activity | Must Have | Pending
Responsive Design | Mobile and desktop layouts | Must Have | Pending
Task Details Page | Full page view for a single task | Must Have | Pending
Search | Search tasks and projects by keyword | Should Have | Pending
User Profile | View and edit own profile | Should Have | Pending
Loading & Error States | Skeleton loaders + error handling UI | Must Have | Pending
🔔 Notifications
Notification System | In-app notifications for task events | Must Have | Pending
Mark as Read | User can dismiss/read notifications | Must Have | Pending
Real-time Push | SignalR push for instant notifications | Should Have | Pending
Email Notifications | Email for invites and important events | Nice to Have | Pending
💬 Real-Time Features
Real-time Notifications | Live push via SignalR without refresh | Must Have | Pending
Team Chat | Per-organization chat room | Should Have | Pending
Online Status | Show who is currently online | Should Have | Pending
Typing Indicator | Show when someone is typing in chat | Nice to Have | Pending
📊 Analytics
Task Completion Stats | Count of done/pending per project | Should Have | Pending
User Activity Charts | Bar chart of task activity over time | Should Have | Pending
Team Productivity View | Tasks per member dashboard | Nice to Have | Pending
⚡ Performance & Quality
API Pagination | All list endpoints paginated | Must Have | Pending
Redis Caching | Cache frequent read queries | Should Have | Pending
DB Indexing | Indexes on FK and frequently filtered columns | Must Have | Pending
Global Error Handling | Consistent ProblemDetails error responses | Must Have | Pending
Input Validation | FluentValidation on all request DTOs | Must Have | Pending
Structured Logging | Serilog with request + error logging | Should Have | Pending
🚀 DevOps & Deployment
Docker Containers | Dockerfiles for API and frontend | Must Have | Pending
CI/CD Pipeline | GitHub Actions for automated build + deploy | Must Have | Pending
Cloud Deployment | API on Render/Railway, frontend on Vercel | Must Have | Pending
Cloud Database | Managed PostgreSQL (Supabase or Neon) | Must Have | Pending
Environment Configs | Secrets via env vars, no hardcoded keys | Must Have | Pending
HTTPS / Domain | Custom domain with SSL | Should Have | Pending